## EXAMPLE
Climate Change Risk Identification & Assessment
CLIMATE VARIABLE: | Current frequency (H, M, L) | Future frequency (H, M, L) | NATURE OF IMPACT - Description (Assumed as a threat, unless stated) | SERVICES AFFECTED | RISK SCORE: |  |  | COVERAGE OF EXISTING PLANS | STATUS | OWNER | RESIDUAL RISK SCORE: |  |  | IDENTIFIED GAPS IN COVERAGE | ACTIONS REQUIRED | TYPE (Win-Win, No Regrets, Low Regrets, Flexible) | ISSUES RAISED/RESOURCES REQUIRED | RESPONSIBILITY | TIMESCALE | TARGET SCORE
[5 empty] | Impact score: 1-4 (A) | Likelihoood score 1-4 (B) | RISK SCORE: Impact X Likelihood (A x B) |  |  |  | Impact score: 1-4 (A) | Likelihoood score 1-4 (B) | RISK SCORE: Impact X Likelihood (A x B)
ADVERSE WEATHER IMPACTS:
Flood | M | H | Increased risk of flooding (all types) could potentially submerge infrastructure, impact on all modes/movements and access to services/employment etc. Potential for wider impact on service delivery, utilities, communications and Emergency Services. | Highways & Transportation | 4 | 3 | 12 | Surface Water Management Plan (SWMP); Strategic Flood Risk Assessment (SFRA) linked to Local Development Framework (LDF); Catchment Flood Management Plans (e.g. Dee, Weaver) | SWMP - Risk Assessment to be completed by June 2011; SFRA/LDF - In Progress; CFMP - xxx. | SWMP - Highways; SFRA/LDF - Planning; CFMP - Environment Agency | 4 | 3 | 12 | Lack of understanding as to capacities/vulnerabilities of United Utilities infrastructure. | Identify critical Infrastruture. Liaise with United Utilities to gain a better understanding of its infrastructure. Educating the public of the risk. Need for a single GIS database to map vulnerabilities (e.g. topography, drainage etc). | Win Win | Check Responsibilities in production of SWMP. Complete initial Risk Assessment. |  | 2011-06-01
|  |  | Increased potential for blockages in gullies and drains will require increased maintenance regimes. | Highways & Transportation | 3 | 3 | 9 |  |  |  | 3 | 3 | 9 |  | Gain a greater awareness of drainage assets and map against flodding hotspots. Develop a revised Monitoring and Maintenance regime to cope with the changing climate. | No Regrets
|  |  | Increased river flows leading to accelerated scour/erosion of bridges/embankments. | Highways & Transportation | 3 | 3 | 9 | Principal Bridge/Structure Inspections | Ongoing | Highways/Highways Agency | 3 | 3 | 9 |  | Increase frequency of inspections | No Regrets
|  |  | Risk to public safety/life caused by flash flooding. | Highways & Transportation | 4 | 1 | 4 | Emergency Flood Response Plans (e.g. Northwich)/Emergency diversion routes. |  | Highways Agency | 4 | 1 | 4 |  | Need for a co-ordinated sandbag policy/Ensure regular inspection and maintenance of drainage system/Review and improve storm sewers.